Quantitative Analysis

Project Management

Student Guide

Thomas Vulsma

thomvu@kku.ac.th

Contents

Project	3

Gantt chart	3

Example 1	3

Example 1	4

Activities on Nodes and Activities on Arrows Diagrams	4

Activities on Nodes	4

Example 2	5

Activities on Arrows	5

Example 3	5

Critical Path Analysis	6

Earliest start:	6

Earliest finish:	6

Latest Start:	6

Latest Finish:	6

Forward Pass	6

Backward Pass	8

Project Crashing	9

Example 4	9

Question 1	11

Question 2	12

Question 3	13

## Project

A project is work which has a clear beginning and a clear end. Most projects consist of multiple activities which have to be completed either simultaneously (at the same time) or sequentially (one after the other). In case a project consists of many activities which are worked on simultaneously and sequentially, it can be very complex and difficult to manage. Therefore, we use project management tools to make the job of managing projects easier and more predictable.

## Gantt chart

A very popular tool is a Gantt chart. This is a table showing activities in rows and time in columns. Horizontal bars show when an activity should start and be completed.

### Example 1

An airline carries out many activities every time an airplane lands at an airport. These activities are shown in the following Gantt chart:

| Passenger Deplaning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Passenger Baggage claim |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baggage Container offload |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fueling Pumping |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fueling Engine injection water |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Container offload |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Servicing Main cabin door |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Servicing Aft cabin Door |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lavatory cleaning Aft, center, forward |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Drinking water Loading |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cleaning First class section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cleaning Economy class section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cargo Container loading |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cabin check |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baggage loading |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Passengers boarding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Time (Minutes) | 0 |  |  |  |  | 10 |  |  |  |  | 20 |  |  |  |  | 30 |  |  |  |  | 40 |

The Gantt chart shows clearly that the entire process of turning an airplane around takes about 40 minutes. It shows what activities are preceded and succeeded by other activities. Also, it shows which activities act as a bottleneck (activities that slow down the entire project).

### Example 1

MPF has the following activities as part of a project to install new equipment in their factory:

| Activity | Description | Time of activity (weeks) | Immediate Predecessor |
| --- | --- | --- | --- |
| A | Build components | 2 | - |
| B | Modify roof and floor | 3 | - |
| C | Construct stack | 2 | A |
| D | Pour concrete and frame | 4 | A, B |
| E | Build burner | 4 | C |
| F | Install pollution control system | 3 | C |
| G | Install air pollution device | 5 | D, E |
| H | Inspect and test | 2 | F, G |

How long will the entire project take (at least)?

The Gantt chart would look something like this.

|  | Time (weeks) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |
| A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Activities on Nodes and Activities on Arrows Diagrams

Very often, Gantt charts cannot contain enough information for the project manager. Therefore, we can use diagrams of nodes and arrows. There are two approaches: AON (Activities On Nodes) and AOA (Activities On Arrows).

## Activities on Nodes

This is the most common method in which each activity is represented by a node (circle) and arrows show the relationship between activities. The disadvantage of AON is that sometimes you need a starting or ending node.

### Example 2

Using the MPF information, we can draw the AON diagram for the installation project.

A

Start

B

C

D

F

E

H

G

## Activities on Arrows

Using this method, activities are represented as arrows and nodes are the connection between activities. The disadvantage of this method is that sometimes you need dummy (fake) activities.

### Example 3

A

B

C

D

F

E

G

H

Taking the same information from Example 1, we can draw the AOA diagram.

## Critical Path Analysis

Some activities in the project are more critical (important) than others because if those critical activities are delayed, the entire project completion will be delayed. Conversely, if critical activities are completed quicker, the entire project will be completed quicker. Therefore, it is important to identify the critical activities of the project using the critical path analysis.

To carry out a critical path analysis we will add more information to each node (or arrow):

B

Name of activity

Duration of activity

2

0

2

1

3

Earliest Finish

Latest Finish

Earliest Start

Latest Start

Earliest start: 		The time (day, week, month, year etc.) when the activity can start at its earliest.

Earliest finish: 	The time when the activity can be finished at earliest (ES+duration).

Latest Start: 	The time when the activity can start at its latest without delaying other activities (latest finish – duration)

Latest Finish: 	The time when the activity can be finished at its latest without delaying other activities.

### Forward Pass

To calculate the completion time of the project, we will fill in all the earliest start and earliest finish numbers. This is called doing the forward pass.

s

0

0

0

0

0

A

0

2

0

0

2

B

0

3

0

0

3

C

2

4

0

0

2

F

4

7

0

0

3

E

4

8

0

0

4

D

3

7

0

0

4

G

8

13

0

0

5

H

13

15

0

0

2

### Backward Pass

To find out what activities are critical (cannot be delayed or else the entire project will be delayed) and which have slack time (have extra time), we do the backward pass by filling in the latest start and latest finish numbers working backwards from the last activity to the first. We can conclude that the critical path is A, C, E, G, H.

s

0

0

0

0

0

A

0

2

0

2

2

B

0

3

1

4

3

C

2

4

2

4

2

F

4

7

10

1334

3

E

4

8

4

8

4

D

3

7

4

8

4

G

8

13

8

13

5

H

13

15

13

15

2

Slack time= 0

Slack time= 0

Slack time= 0

Slack time= 6

Slack time= 0

Slack time= 0

Slack time=1

Slack time= 1

Slack time= 0

## Project Crashing

Crashing a project means that you spend extra money to complete your project quicker. You do this by shortening activities on the critical path. Only by shortening the critical path you can shorten the completion time of the project.

The first step in project crashing is to calculate the crash cost of one period for all activities. The second step is to select the cheapest activity to crash by one period (on the critical path). Keep on crashing the cheapest activities until you have reached your target completion time.

### Example 4

Using the same activities as example 3, the following information is given about cost of each activity. The normal completion time is 15 weeks, but we want to complete the project in only 13.

| Activity | Normal Time | Crash Time | Normal Cost | Crash Cost | Crash Cost Per Week |
| --- | --- | --- | --- | --- | --- |
| A | 2 | 1 | 22,000 | 22,750 | 750 |
| B | 3 | 1 | 30,000 | 34,000 | 2,000 |
| C | 2 | 1 | 26,000 | 27,000 | 1,000 |
| D | 4 | 3 | 48,000 | 49,000 | 1,000 |
| E | 4 | 2 | 58,000 | 58,000 | 1,000 |
| F | 3 | 2 | 30,000 | 30,500 | 500 |
| G | 5 | 2 | 80,000 | 84,500 | 1,500 |
| H | 2 | 1 | 16,000 | 19,000 | 3,000 |

Now we chose the first activity to crash:

The cheapest activity on the critical path is A and we can crash this activity by only one week. So we crash it in our diagram and see what changes.

After crashing activity A, we crash the next cheapest activity on the critical path: G.

s

0

0

0

0

0

A

0

1

0

1

1

B

0

3

0

3

3

C

1

3

1

3

2

F

3

6

8

1134

3

E

3

7

3

7

4

D

3

7

3

7

4

G

7

11

7

11

4

H

11

13

11

13

2

Slack time= 0

Slack time= 0

Slack time= 0

Slack time= 6

Slack time= 0

Slack time= 0

Slack time=0

Slack time= 0

Slack time= 0

### Question 1

Use Activities on Nodes (AON) and Activities on Arrows (AOA) to draw the project diagram for the following project.

| Activity | Time (weeks) | Predecessor |
| --- | --- | --- |
| J | 10 | - |
| K | 8 | - |
| L | 6 | J |
| M | 3 | J |
| N | 2 | K, M |
| O | 7 | L, N |
| P | 5 | K, M |

### Question 2

DFA is designing and producing a race car. The following activities have to be done to complete the project. Create an AON network for these activities. Do the forward pass and backward pass to determine the critical path and slack times.

| Activity | Immediate Predecessor | Time (weeks) |
| --- | --- | --- |
| A | - | 6 |
| B | - | 7 |
| C | A | 3 |
| D | A | 2 |
| E | B | 4 |
| F | B | 6 |
| G | C, E | 10 |
| H | C, E | 7 |

### Question 3

A hot dog shop is building a new kitchen. The following activities are required.

| Activity | Normal Time | Crash Time | Normal Cost | Crash Cost | Immediate Predecessor |
| --- | --- | --- | --- | --- | --- |
| A | 3 | 2 | 1000 | 1600 | - |
| B | 2 | 1 | 2000 | 2700 | - |
| C | 1 | 1 | 300 | 300 | - |
| D | 7 | 3 | 1300 | 1600 | A |
| E | 6 | 3 | 850 | 1000 | B |
| F | 2 | 1 | 4000 | 5000 | C |
| G | 4 | 2 | 1500 | 2000 | D, E |

- What is the project completion date? What is the critical path?

- How much does it cost to crash the project to 10 weeks?

- How much does it cost to crash the project to 7 weeks?

- Can you crash the project to 6 weeks?